## Sheet1
STANTEC COST ESTIMATE
DDA BICYCLE & PEDESTRIAN MOBILITY IMPROVEMENTS
TRANSPORTATION ENHANCEMENT GRANT
STANTEC Project No. 216710012
2017-02-15
|  | QUANT. | UNIT | ESTIMATED UNIT PRICE | Contractor ESTIMATED AMOUNT
Project 2 - SE 1st Street Intersections with S. Miami Ave./SE 1st Ave./SE 2nd Ave. and Flagler Street with SE 3rd Ave.
2.01 | Traffic Pedestrian Head | 50 | EA. |  | 0
2.03 | Additional/Retrofit Exist. Bracket | 16 | EA. |  | 0
2.04 | Pavement Marking Crosswalk (white) (12"), Includes Sandblasting | 674 | L.F. |  | 0
2.05 | Pavement Marking Crosswalk (white) (24"), Includes Sandblasting | 525 | L.F. |  | 0
2.06 | Remove and Reconstruct Pedestrian Conc. Ramp | 2450 | S.F. |  | 0
2.07 | Reconstruct Conc. Curb & Gutter | 40 | L.F. |  | 0
2.07 | Signal Modification | 4 | PI |  | 0
|  |  |  | Project 3 Sub-Total | 0
Project 3 - Various Roadways Bicycle Facility Improvements
3.01 | Thermoplastic (white) (solid) (6") | 6385 | L.F. |  | 0
3.02 | Thermoplastic (white) (solid) (18") | 440 | L.F. |  | 0
3.03 | Thermoplastic (white) (solid) (6") 2'-4' Skip | 309 | L.F. |  | 0
3.04 | Thermoplastic (white) (arrow) | 1 | EA. |  | 0
3.05 | Thermoplastic (white) (bike lane symbol) | 8 | EA. |  | 0
3.06 | Thermoplastic (white) (bike sharrow symbol) | 80 | EA. |  | 0
3.06 | R3-16 Sign Assembly (Bicycle Lane Ahead Sign) | 1 | EA. |  | 0
3.07 | R3-17 Sign Assembly (Bicycle Sign) | 2 | EA. |  | 0
3.08 | R3-17/R3-17b Sign Assembly (Bicycle sign with End Sign) | 1 | EA. |  | 0
3.09 | R4-11 Sign Assembly (Bike Sharing Sign) | 11 | EA. |  | 0
|  |  |  | Project 3 Sub-Total | 0
Project 4 thru 7 - Intersection Pedestrian Improvements
4.01 | Remove and Reconstruct Pedestrian Conc. Ramp | 2400 | S.F. |  | 0
4.02 | Detectable Warning Surface | 224 | S.F. |  | 0
4.03 | Pavement Marking Crosswalk (white) (12"), Includes Sandblasting | 2520 | L.F. |  | 0
4.04 | Thermoplastic (white) (solid) (24") | 950 | L.F. |  | 0
4.05 | Remove and relocate Fire Hydrant | 1 | EA. |  | 0
4.06 | Reconstruct Conc. Curb & Gutter | 372 | L.F. |  | 0
|  |  |  | Project 4 Sub-Total | 0
Project 9 Brickell Ave
5.01 | Remove and Reconstruct Pedestrian Conc. Ramp | 900 | S.F. |  | 0
5.02 | Detectable Warning Surface | 32 | S.F. |  | 0
5.03 | Pavement Marking Crosswalk (white) (12"), Includes Sandblasting | 450 | L.F. |  | 0
5.04 | Thermoplastic (white) (solid) (24") | 400 | L.F. |  | 0
5.05 | R1-2 Sign Assembly (Pedestrian) | 4 | EA. |  | 0
5.06 | R1-6A Sign Assembly (State Law Stop for Pedestrian) | 2 | EA. |  | 0
5.06 | R1-5C Sign Assembly (Stop here for Pedestrian) | 4 | EA. |  | 0
5.07 | Reconstruct Conc. Curb & Gutter | 85 | L.F. |  | 0
|  |  |  | Project 4 Sub-Total | 0
Miscellaneous
|  |  |  | Overall Sub-Total | 0
5.01 | Mobilization | 1 | L.S. |  | 0
5.02 | Utility Exploration | 1 | L.S. |  | 0
5.03 | Performance & Payment Bond | 1 | L.S. |  | 0
5.04 | Contingency | 1 | L.S. |  | 0
|  |  |  | Misc. Sub-Total | 0
|  |  |  | Overall Total | 0

## Sheet3
DDA BICYCLE & PEDESTRIAN MOBILITY IMPROVEMENTS
TRANSPORTATION ENHANCEMENT GRANT
STANTEC Project No. 216710012
2017-02-15
|  | QUANT. | UNIT | UNIT COST | Contractor ESTIMATED AMOUNT
Project 2 - SE 1st Street Intersections with S. Miami Ave./SE 1st Ave./SE 2nd Ave. and Flagler Street with SE 3rd Ave.
2.01 | Traffic Pedestrian Head | 50 | EA. |  | 0
2.03 | Additional/Retrofit Exist. Bracket | 16 | EA. |  | 0
2.04 | Pavement Marking Crosswalk (white) (12"), Includes Sandblasting | 674 | L.F. |  | 0
2.05 | Pavement Marking Crosswalk (white) (24"), Includes Sandblasting | 525 | L.F. |  | 0
2.06 | Remove and Reconstruct Pedestrian Conc. Ramp | 2450 | S.F. |  | 0
2.07 | Reconstruct Conc. Curb & Gutter | 40 | L.F. |  | 0
2.07 | Signal Modification | 4 | PI |  | 0
|  |  |  | Project 3 Sub-Total | 0
Project 3 - Various Roadways Bicycle Facility Improvements
3.01 | Thermoplastic (white) (solid) (6") | 6385 | L.F. |  | 0
3.02 | Thermoplastic (white) (solid) (18") | 440 | L.F. |  | 0
3.03 | Thermoplastic (white) (solid) (6") 2'-4' Skip | 309 | L.F. |  | 0
3.04 | Thermoplastic (white) (arrow) | 1 | EA. |  | 0
3.05 | Thermoplastic (white) (bike lane symbol) | 8 | EA. |  | 0
3.06 | Thermoplastic (white) (bike sharrow symbol) | 80 | EA. |  | 0
3.06 | R3-16 Sign Assembly (Bicycle Lane Ahead Sign) | 1 | EA. |  | 0
3.07 | R3-17 Sign Assembly (Bicycle Sign) | 2 | EA. |  | 0
3.08 | R3-17/R3-17b Sign Assembly (Bicycle sign with End Sign) | 1 | EA. |  | 0
3.09 | R4-11 Sign Assembly (Bike Sharing Sign) | 11 | EA. |  | 0
|  |  |  | Project 3 Sub-Total | 0
Project 4 thru 7 - Intersection Pedestrian Improvements
4.01 | Remove and Reconstruct Pedestrian Conc. Ramp | 2400 | S.F. |  | 0
4.02 | Detectable Warning Surface | 224 | S.F. |  | 0
4.03 | Pavement Marking Crosswalk (white) (12"), Includes Sandblasting | 2520 | L.F. |  | 0
4.04 | Thermoplastic (white) (solid) (24") | 950 | L.F. |  | 0
4.05 | Remove and relocate Fire Hydrant | 1 | EA. |  | 0
4.06 | Reconstruct Conc. Curb & Gutter | 372 | L.F. |  | 0
|  |  |  | Project 4 Sub-Total | 0
Project 9 Brickell Ave
5.01 | Remove and Reconstruct Pedestrian Conc. Ramp | 900 | S.F. |  | 0
5.02 | Detectable Warning Surface | 32 | S.F. |  | 0
5.03 | Pavement Marking Crosswalk (white) (12"), Includes Sandblasting | 450 | L.F. |  | 0
5.04 | Thermoplastic (white) (solid) (24") | 400 | L.F. |  | 0
5.05 | R1-2 Sign Assembly (Pedestrian) | 4 | EA. |  | 0
5.06 | R1-6A Sign Assembly (State Law Stop for Pedestrian) | 2 | EA. |  | 0
5.06 | R1-5C Sign Assembly (Stop here for Pedestrian) | 4 | EA. |  | 0
5.07 | Reconstruct Conc. Curb & Gutter | 85 | L.F. |  | 0
|  |  |  | Project 4 Sub-Total | 0
Miscellaneous
|  |  |  | Overall Sub-Total | 0
5.01 | Mobilization | 1 | L.S. |  | 0
5.02 | Maintenance of Traffic | 1 |  |  | 0
5.03 | Traffic Control Officer (Allowance) | 1 |  |  | 0
5.04 | Owner's Permit Allowance | 1 |  |  | 0
|  |  |  | Misc. Sub-Total | 0
0
TOTAL BID CONSTRUCTION COST